## Guide
Product Backlog:
- It is a priority list of user requirements to develop a software or an application.
- Product owner owns this document
- Product owner prioritize the user requirements based on the customer feedback or business value
- The user requirements are written in the form of user stories which are explained in detail
- The product backlog is like a repository that act as an input to the sprint backlog.
- In simple sentence, product backlog is simply a wish list for an application.
- Update the product backlog on regular basis
Sprint Backlog
- It is the subset of the product backlog
- Each sprint includes user stories from the product backlog
- Product owner sets the sprint goal for the team
- The team then pick the user stories to fulfill those goals
- The user stories that are moved to sprint are then owned by the scrum team
- It is important to put the sprint goals as static as possible.
- During sprint planning, the team pics the recently prioritized user stories from the product backlog.
- Spring backlog is an output of the sprint planning meeting
User Story
A user story is simply a description of a feature that is described in users own words. Therefore, it is extremely important to recognize the users. A user is the user of a system. When writing user stories, it is also beneficial to explain the business value first.
The user story are written as:
As a (user), I want to ..... so that ......
Examples:
As an administrator, i want to be able to create new user accounts.
As a student, I should be able to upload assignemtns in the Moodle.
As a student, I want to be able to change my password.
Example with business value (recommended)
In order to find the cheapest price, as a buyer i want to compare prices.
In order to check grades in quick time, as a student I want to be able to see all my grades in one page.
Story Points
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a vlaue 1 and other other story 2. The one with the value 2 means that it requires dobule effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## Product Backlog
Product Backlog - Project Title
User Story | Story Point(s) | Priority
As a voter, I want access to the front page. | 6 | 2
As a voter, I want to be able to use website in mobile. | 5 | 3
As a voter, I want to be able to see all candidates. | 4 | 1
As a voter, I want to see more information about the party so I can get a better idea of the candidates. | 4 | 2
As a voter, I want to be able to see and answer all the questions. | 4 | 1 | Priority
As a voter, I want to be able to get more information or possible clarification for the questions. | 2 | 1 | 1 = high priority
As a voter, I want to be able to see my progress and get who are best candidates for me at this point of progression. | 6 | 1 | 2 = medium priority
As a voter, I want to be able to get more information about partys canditates. | 5 | 1 | 3 = low priority
As a voter, I want to be able to see how candidates have answered for different questions. | 4 | 1
As a voter, I should be able to go back and forth between the questions, so that I can change my answers. | 2 | 1 | Story Points
As a voter, I should be able to submit my answers, so that I can see the candidates best suited for me. | 2 | 1 | 1 = very easy
As an admin, I need to be able to login. | 4 | 1 | 10 = very hard
As an admin, I need to be able change registered canditates informations. | 3 | 1
As an admin, I need to be able delete registered canditates. | 4 | 1
As an admin, I need to be able create new registered canditates. | 4 | 1
As an admin, I need to be able to edit the questions. | 5 | 1
As an admin, I need to be able to delete the questions. | 3 | 1
As an admin, I need to be able to add the questions. | 4 | 1
As a registered candidate, I want to be able to change my personal information. | 6 | 3
As a registered candidate, I should be able to answer to questions. | 6 | 1
As a registered candidate, I should be able to login. | 7 | 1
As a voter, I want to be able to see how candidates have answered for different questions. | 4 | 1
As a voter, I want the pages to be clear and easy to navigate. | 5 | 2

## Sprint 1 Backlog
Sprint Backlog : Sprint 1
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
As a voter, I want access to the front page.
Task : HTML | 6 | Laura | Ready | 2 | 1 | 0.15 | 3.5 | 1
Task : CSS | 4 | Laura | Ready | 0.5 | - | 4.5 | 2 | 1
Task : JS | 4 | Laura | Ready | 1 | 2 | 0.3 | 2 | 1
Task : Bootstrap | 2 | Laura | Ready | 2 | 1 | 1.5 | 0.5 | 1
As a voter, I want to be able to use website in mobile.
Task : Testing responsivity | 2 | Laura | Ready | 0.5 | 0.5 | 2 | 1 | 3
Task : Editing Bootstrap | 4 | Niklas | Ready | 3 | 0.3 | 1 | 2 | 3
Task : Implementation of selfmade code on a ready-made basis | 4 | Niko | Ready | 3 | 3 | 2 | 3 | 1
As a voter, I want to be able to see all candidates.
Task : Creating the database | 6 | Laura, Niko, Niklas | Ready | 1 | 2 | 1 | 3 | 1.5
Task : Adding candidates into the database | 4 | Laura, Niko, Niklas | Ready | 3 | 1.5 | 1 | - | -
Task : Fetching data from the database | 7 | Laura, Niko, Niklas | Ready | 1 | 0.5 | 1 | - | -
Task : Creating a list of candidates | 4 | Laura, Niko, Niklas | Ready | 1 | 2 | 0.5 | 0.5 | -
As a voter, I want to see more information about the party so I can get a better idea of the candidates.
Task : Constituency selection | 4 | Niklas | Not started | - | - | - | - | -
Task : Hover list of election parties | 3 | Niklas | Not started | - | - | - | - | -
Task : Information box | 1 | Niklas | Not started | - | - | - | - | -
As a voter, I want to be able to see and answer all the questions.
Task : Creating the database | 6 | Laura, Niko, Niklas | Ready | 1 | 2 | 1 | 3 | 1.5
Task : Adding questions into the database | 4 | Laura, Niko, Niklas | Ready | 3 | 1.5 | 1 | - | -
Task : Fetching data from the database | 7 | Laura, Niko, Niklas | Ready | - | - | - | 1 | 1
Task : Creating a list of questions | 4 | Laura, Niko, Niklas | Ready | - | - | - | 1 | 2
As a voter, I want to be able to get more information or possible clarification for the questions.
Task : Adding more details tag for every survey | 2 | Niko | Not started | - | - | - | - | -
Task : Fetching information from database | 4 | Niko | Not started | - | - | - | - | -
TOTAL |  |  |  | 22 | 17.3 | 16.95 | 22.5 | 17

## Sprint Meetings
Sprint Planning | Participants
Week 12 | Laura Mattila | Niko Rantala | Niklas Sundell
HAMK | X | X | X | If physically present mark X
2022-03-19 | Installing and testing all needed softwares and starting the Scrum documentation in Teams.
Week 13 | Laura Mattila | Niko Rantala | Niklas Sundell
Teams Meeting | Online | Online | Online
2022-03-28 | Starting the project by making repository and branches to all members. The next is implementation of website layout with HTML, CSS and JavaScript. We use Bootstrap library with our site.
Week 14 | Laura Mattila | Niko Rantala | Niklas Sundell
Teams Meeting | Online | Online | Online
2022-04-04 | Continuation of the project by adding new features to the site. We create a database to help with testing and inspecting the query result. Our features include adding, editing, and deleting a question. Every question is also retrieved from the database.
Week 15 | Laura Mattila | Niko Rantala | Niklas Sundell
Teams Meeting | Online | Online | Online
2022-04-11 | Finishing the first side of the module by adjusting the project to its final form. We also review each step and check the codes. Further development of the project will take place on the other side of the module.
Sprint Planning
- Sprint planning is done at the beginning of each sprint with the participation of the entire scrum team.
- During the sprint planning meeting, the scrum team decides what will be delivered at the end of the sprint by turning the highest priority features on the product backlog into detailed tasks.
- This process creates the sprint backlog.
- The sprint planning meeting focuses on answering two main questions:
1) What needs to be done? and
2) How will it be done?
The sprint goal is also defined during the sprint planning meeting.
Src: https://www.lucidchart.com/

## Sprint 2 Backlog
Sprint Backlog : Sprint 2
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
As an admin, I need to be able to login.
Task : HTML-login form | 6 | Niko | Ready | 1 | 0.5 | - | - | -
Task : CSS | 4 | Niko | Ready | 0.5 | 0.3 | - | - | -
Task : Bootstrap | 2 | Niko | Ready | 1 | 0.3 | - | - | -
Task : Admin database | 5 | Niko | Ongoing | 1 | - | 0.5 | - | -
As an admin, I need to be able to edit the questions.
Task : Edit questions servlet | 4 | Niklas | Ready | 1.5 | 1.5 | 1 | - | -
Task : Edit questions JSP | 3 | Niklas | Ready | 1 | 1 | 2 | - | -
Task : Question list | 5 | Niklas | Ready | 0.5 | 0.5 | 2 | - | -
Task : SQL-query | 3 | Niklas | Ready | 1 | - | 1 | - | -
As an admin, I need to be able to delete the questions.
Task : Delete questions servlet | 4 | Laura, Niklas, Niko | Ready | 1 | 1.5 | 2 | - | -
Task : Delete questions JSP | 3 | Laura, Niklas, Niko | Ready | 0.5 | 1 | 2 | - | -
Task : Question list | 5 | Laura, Niklas, Niko | Ready | 0.45 | 0.5 | 0.5 | - | -
Task : SQL-query | 3 | Laura, Niklas, Niko | Ready | 0.15 | 1 | 0.5 | - | -
As an admin, I need to be able to add the questions.
Task : Add questions servlet | 7 | Laura | Ready | - | - | 1 | 0.5 | 0.45
Task : Add questions JSP | 8 | Laura | Ready | - | - | 1 | 0.45 | 2
Task : Question list | 5 | Laura | Ready | - | - | 0.5 | 1 | 0.5
Task : SQL-query | 6 | Laura | Ready | - | - | 0.5 | 1 | 1
As an admin, I want the pages to be clear and easy to navigate.
Task : Testing responsivity | 5 | Laura, Niklas, Niko | Ongoing | - | - | - | - | 0.45
Task : Editing Bootstrap | 6 | Laura, Niklas, Niko | Ongoing | - | - | - | - | 1
Task : Editin CSS | 6 | Laura, Niklas, Niko | Ongoing | - | - | - | - | 1
Task : Editin HTML | 3 | Laura, Niklas, Niko | Ongoing | - | - | - | - | 0.5
TOTAL |  |  |  | 9.6 | 8.1 | 14.5 | 2.95 | 6.9